## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Defects
| Table 1 | Defects
Defects
| Table 1 | Defects
Sheet2
| Table 1 | Sheet2

## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Id | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Mrittika Das | 2025-08-23 | Validating email field by entering registered user's email in Sign up page.When we entered the email that already exists.The expected result is "Email already exists!" but the page is again registering the user | DT001 | Gayathri | Standards | Bug is accepted and fixes is in progress | 2025-08-24 | Open | No
2 | Mrittika Das | 2025-08-23 | Validating Username field by entering a registered user's Username. When we entered the username that already exists in the database.The expected result is "Username already exists!" but the Sign up page is again registering the user | DT002 | Gayathri | Standards | Bug is accepted and fixes is in progress | 2025-08-24 | Open | No
3 | Mrittika Das | 2025-08-23 | Validating confirm password field by entering invalid password in Sign up page.When we entered the password then we have to again re-enter the same password in Confirm Password field .If we re-enter the invalid password in Confirm Password field also the Sign Up page is registering the user. | DT003 | Gayathri | Standards | Bug is accepted and fixes is in progress | 2025-08-24 | Open | No
4 | Abhigna | 2025-08-23 | Validating forgot password link and entering valid details.When we entered the email id in forgot password field and click on Get OTP the OTP is not sent to registered email | DT004 | Gayathri | Standards | Bug is accepted and fixes is in progress | 2025-08-24 | Open | No
5 | Abhigna | 2025-08-23 | Validating the re-enter passdword field by entering different password in the required field in the Forgot Password page.The expected result is "Password doesn't match" but the page is showing a message saying "Reset Password Succesfully" | DT005 | Gayathri | Standards | Bug is accepted and fixes is in progress | 2025-08-24 | Open | No
6 | Abhigna | 2025-09-14 | Validating user verification by providing some details incase user is not verified when we entered all the valid details in Sign Up page then The pages need to navigate to the User verification page but the page showing the message Username already taken | DT006 | Mrittika | Standards | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
7 | Mrittika Das | 2025-09-14 | Validating the responsiveness of the Sign Up page and css issue. | DT007 | Gayathri | User Interface | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
8 | Gayathri | 2025-09-14 | Validating the login page by giving the details of the unverified user.When we entered the invalid email and password then click on login to continue button then the expected result is "navigates to the Sign Up page" but the page is showing a message "An email has already been sent to verify your acccount" | DT008 | Mrittika | Standards | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
9 | Chirag | 2025-09-14 | Validating that the user should be redirected to the profile page without any error.After logging in then go to the My Profile page.Here expected result is"Profile should be visible to the User" but the page is showing some "Uncaught runtime errors" | DT009 | Abhigna | Logical | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
10 | Chirag | 2025-09-14 | Validating that the user should not be able to left blank required fields.Go to My Profile and then go to the Edit profile page then click on update profile page then the expected result is"Fill all the required fields" but the page is showing a message "Update profile successfully" | DT010 | Abhigna | Standards | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
11 | Chirag | 2025-09-14 | Validating that the user should not be able to save a profile page with invalid data.When we entered the invalid details of the user in the edit profile page.The expected result is "Invalid data" but the result we got is "Update profile successfully" | DT011 | Abhigna | Standards | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
12 | Chirag | 2025-09-14 | Validating the exercise name field with invalid details.When we entered the invalid details in the exercise field and click on save.The page is showing "Something went wrong.Please try again later" but the expected result is "Invalid data" | DT012 | Mrittika | Standards | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
13 | Chirag | 2025-09-14 | Validating the diet name field with invalid details.When we entered the invalid details in the diet field.The page has to show a message"Invalid data" but the page is showing "Something went wrong.Please try again later" | DT013 | Mrittika | Standards | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
14 | Harsha | 2025-09-14 | Validating the responsiveness of the Login page and css issue. | DT014 | Pranay | User Interface | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
15 | Harsha | 2025-09-14 | Validating the responsiveness of the Forgot Password page and css issue. | DT015 | Pranay | User Interface | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
16 | Harsha | 2025-09-14 | Validating the responsiveness of the Landing page and css issue. | DT016 | Pranay | User Interface | Bug is accepted and fixes is in progress | 2025-09-15 | Open | No
17 | Debosmita | 30-09-2025 | Validating reset password link and entering valid details.When we entered new password then password is not resetting, shows error “Password cannot be more than 8 characters long.”, Even entering valid password | DT017 | Abhigna | Standards | Bug is accepted and fixes is in progress | 30-09-2025 | Open | No
18 | Debosmita | 30-09-2025 | Validating responsiveness of Exercise page and updating CSS | DT018 | Dhivya | Standards | Bug is accepted and fixes is in progress | 30-09-2025 | Open | No
19 | Debosmita | 30-09-2025 | Validating responsiveness of Tables of Mobile view | DT019 | Dhivya | Standards | Bug is accepted and fixes is in progress | 30-09-2025 | Open | No
20 | Debosmita | 30-09-2025 | Validating responsiveness of Graph | DT020 | Dhivya | Standards | Bug is accepted and fixes is in progress | 30-09-2025 | Open | No

## Sheet2
Logical
User Interface
Maintainability
Standards
Others